{"text_format":"3","workbook":"xlsx","n_sheets":13,"sheets":["档案整理费","会议室租赁费","安全生产监督执法专项经费","兰州新区化工园区企业专业化隐患排查治理项目","安全生产标准化评审与危化品建设项目安全审查费用专项资金","应急救援综合能力提升项目","气象服务专项经费","甘肃省自然灾害应急能力提升工程基层防灾项目经费","甘肃省自然灾害应急能力提升工程基层防灾项目（本级配套）","”陇原砺剑.2023“演习","2023年安全生产及应急专项","危险化学品安全知识竞赛及化工园区安全技能实训基地宣传推广补助资","公共安全监管能力提升项目"],"read":"whole","date_system":"1900"}

{"sheet":"档案整理费","index":0,"n_rows":30,"n_cols":14,"rows_kept":30,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,27,0],[16,1,18,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,1,23,2],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,3,22,4],[21,5,21,6],[22,5,22,6],[23,3,23,4],[23,5,23,6],[24,1,26,2],[24,3,24,4],[24,5,24,6],[25,3,25,4],[25,5,25,6],[26,3,26,4],[26,5,26,6],[27,1,27,2],[27,3,27,4],[27,5,27,6],[28,0,28,13],[29,0,29,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"2024年档案整理费"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"60000",null,"60000",null,"59913.8",null,"10","99.85","9.98"]
[null,null,"其中：财政拨款",null,"60000",null,"60000",null,"59913.8",null,"-","99.85","9.98"]
[null,null,"上年结转资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[null,null,"其他资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,"已完成"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"整理2022年文书档案预计5000件、整理项目档案500卷并完成数字化加工，按照要求移交至档案馆。",{"$nulls":5},"按照《兰州新区党工委办公室关于开展新区各类档案资料收集整理归档工作的通知》文件要求，我局计划于2024年整理2022年文书档案5000件，整理项目档案500卷，数字化加工20000页，截止12月底已完成该项工作，支付5.99万元。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=6万元","5.99","6.67","万元","100.00%","6.67",""]
[{"$nulls":3},"社会成本指标",null,"电子化管理率",null,">=90%","90","6.67","%","100.00%","6.67",""]
[{"$nulls":3},"生态成本指标",null,"节约率",null,">=90%","90","6.66","%","100.00%","6.66",""]
[null,"产出指标",null,"数量指标",null,"整理文书档案",null,">=50000件","50000","8","件","100.00%","8",""]
[{"$nulls":5},"整理项目档案",null,">=500卷","500","8","卷","100.00%","8",""]
[{"$nulls":3},"质量指标",null,"整理文书档案合格率",null,">=100%","100","8","%","100.00%","8",""]
[{"$nulls":5},"整理项目档案合格率",null,">=100%","100","8","%","100.00%","8",""]
[{"$nulls":3},"时效指标",null,"文件资料整理及时性",null,"及时","100%-80%(含)","8","","100%","7.2",""]
[null,"效益指标",null,"经济效益指标",null,"档案管理规范性",null,"完善","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"社会效益指标",null,"完善档案整理管理体系",null,"完善","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态效益指标",null,"完善档案电子化管理",null,"完善","100%-80%(含)","6.66","","100%","5.99",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"群众满意度",null,">=90%","90","10","%","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"97.18"]

{"sheet":"会议室租赁费","index":1,"n_rows":30,"n_cols":14,"rows_kept":30,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,27,0],[16,1,17,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,1,23,2],[18,3,19,4],[18,5,18,6],[19,5,19,6],[20,3,21,4],[20,5,20,6],[21,5,21,6],[22,3,23,4],[22,5,22,6],[23,5,23,6],[24,1,26,2],[24,3,24,4],[24,5,24,6],[25,3,25,4],[25,5,25,6],[26,3,26,4],[26,5,26,6],[27,1,27,2],[27,3,27,4],[27,5,27,6],[28,0,28,13],[29,0,29,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"2024年会议室租赁费"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"110000",null,"110000",null,"100000",null,"10","90.9","9.09"]
[null,null,"其中：财政拨款",null,"110000",null,"110000",null,"100000",null,"-","90.9","9.09"]
[null,null,"上年结转资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[null,null,"其他资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,"已完成"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"保障每季度组织召开安委会会议一次，重大节日组织开展节前安全生产警示会议4次，开展危险化学品安全生产推进会议4次。",{"$nulls":5},"截止12月底，共召开兰州新区安委会会议4次，支付4万元，召开安全生产警示交易会议4次，支付4万元，召开危险化学品安全生产推进会议两次，支付2万元，共支付10万元。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=11万元","10","10","万元","100.00%","10",""]
[{"$nulls":3},"社会成本指标",null,"减少事故发生",null,"减少","100%-80%(含)","10","","100%","9",""]
[null,"产出指标",null,"数量指标",null,"安委会会议召开次数",null,">=4次","4","6.67","次","100.00%","6.67",""]
[{"$nulls":5},"危险化学品安全生产推进会议召开次数",null,">=4次","4","6.67","次","100.00%","6.67",""]
[{"$nulls":3},"质量指标",null,"安委会会议受众人数",null,">=800人","756","6.67","人","94.50%","6.3",""]
[{"$nulls":5},"危险化学品安全生产推进会议受众人数",null,">=800人","658","6.67","人","82.25%","5.49",""]
[{"$nulls":3},"时效指标",null,"及时完成会场布置",null,"及时","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":5},"及时完成会议",null,"及时","100%-80%(含)","6.65","","100%","5.98",""]
[null,"效益指标",null,"经济效益指标",null,"提升安全生产监督管理水平",null,"提升","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"社会效益指标",null,"提高企业乃至全民安全意识",null,"提高","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态效益指标",null,"提升整体安全生产水平",null,"提升","100%-80%(含)","6.66","","100%","5.99",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"服务企业满意度",null,">=90%","90","10","%","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"93.19"]

{"sheet":"安全生产监督执法专项经费","index":2,"n_rows":37,"n_cols":14,"rows_kept":37,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,34,0],[16,1,17,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,1,31,2],[18,3,22,4],[18,5,18,6],[19,5,19,6],[20,5,20,6],[21,5,21,6],[22,5,22,6],[23,3,27,4],[23,5,23,6],[24,5,24,6],[25,5,25,6],[26,5,26,6],[27,5,27,6],[28,3,31,4],[28,5,28,6],[29,5,29,6],[30,5,30,6],[31,5,31,6],[32,1,33,2],[32,3,32,4],[32,5,32,6],[33,3,33,4],[33,5,33,6],[34,1,34,2],[34,3,34,4],[34,5,34,6],[35,0,35,13],[36,0,36,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"安全生产监督执法专项经费"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"910000",null,"910000",null,"909778.48",null,"10","99.97","9.99"]
[null,null,"其中：财政拨款",null,"910000",null,"910000",null,"909778.48",null,"-","99.97","9.99"]
[null,null,"上年结转资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[null,null,"其他资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,"已完成"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"充分发挥安全生产专家技术支撑作用,预防和减少一般事故、坚决遏制较大以上事故的安全风险防控体系更加牢固。",{"$nulls":5},"该项目为权利推动安全生产专项治理三年行动和新型应急管理“六大体系” 建设深入开展，充分发挥安全生产专家技术支撑作用，预防和减少一般事故，2024年组织检查150余次，宣传培训活动6次，应急演练7场，该项目预算合理，基本与绩效目标一致。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=91万元","90.98","10","万元","100.00%","10",""]
[{"$nulls":3},"社会成本指标",null,"提升整体安全生产水平",null,"提升","100%-80%(含)","10","","100%","9",""]
[null,"产出指标",null,"数量指标",null,"安全生产事故处理",null,">=100%","100","2.86","%","100.00%","2.86",""]
[{"$nulls":5},"采购设备",null,">=1批","1","2.86","批","100.00%","2.86",""]
[{"$nulls":5},"开展安全检查服务",null,">=150次","150","2.86","次","100.00%","2.86",""]
[{"$nulls":5},"开展综合性演练",null,">=7次","7","2.86","次","100.00%","2.86",""]
[{"$nulls":5},"专家指导服务工作",null,">=150次","150","2.86","次","100.00%","2.86",""]
[{"$nulls":3},"质量指标",null,"设备合格率",null,">=100%","100","2.86","%","100.00%","2.86",""]
[{"$nulls":5},"业务培训等达标率",null,">=100%","100","2.86","%","100.00%","2.86",""]
[{"$nulls":5},"应急演练达标率",null,">=100%","100","2.86","%","100.00%","2.86",""]
[{"$nulls":5},"专家参与安全检查达标率",null,">=100%","100","2.86","%","100.00%","2.86",""]
[{"$nulls":5},"专家指导服务达标率",null,">=100%","100","2.86","%","100.00%","2.86",""]
[{"$nulls":3},"时效指标",null,"安全生产大检查完成及时性",null,"及时","100%-80%(含)","2.86","","100%","2.57",""]
[{"$nulls":5},"事故调查处理及时性",null,"及时","100%-80%(含)","2.86","","100%","2.57",""]
[{"$nulls":5},"业务培训开展及时性",null,"及时","100%-80%(含)","2.82","","100%","2.54",""]
[{"$nulls":5},"应急演练及时性",null,"及时","100%-80%(含)","2.86","","100%","2.57",""]
[null,"效益指标",null,"经济效益指标",null,"提升安全生产监督管理水平",null,"提升","100%-80%(含)","10","","100%","9",""]
[{"$nulls":3},"社会效益指标",null,"提高企业乃至全民安全发展理念",null,"提升","100%-80%(含)","10","","100%","9",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"服务企业满意度",null,">=90%","90","10","%","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"95.85"]

{"sheet":"兰州新区化工园区企业专业化隐患排查治理项目","index":3,"n_rows":30,"n_cols":14,"rows_kept":30,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,27,0],[16,1,18,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,1,24,2],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,3,22,4],[21,5,21,6],[22,5,22,6],[23,3,24,4],[23,5,23,6],[24,5,24,6],[25,1,26,2],[25,3,25,4],[25,5,25,6],[26,3,26,4],[26,5,26,6],[27,1,27,2],[27,3,27,4],[27,5,27,6],[28,0,28,13],[29,0,29,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"兰州新区化工园区企业专业化隐患排查治理项目"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"2000000",null,"2000000",null,"2000000",null,"10","100","10"]
[null,null,"其中：财政拨款",null,"2000000",null,"2000000",null,"2000000",null,"-","100","10"]
[null,null,"上年结转资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[null,null,"其他资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,"已完成"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"聘请第三方专业机构及行业专家对化工园区投产企业开展2轮专业化隐患排查治理（隐患排查和复查问题整改）；评选2家自动化水平高、隐患治理较好的企业给予奖励，树立典范，引导园区其他企业对表对标，加大自动化改造力度，提高自动化水平，排查治理隐患，降低安全风险；借助第三方专业机构力量，通过全方位的专业化隐患排查治理，有效防控各类安全风险，遏制各类生产安全事故，保障化工园区在安全中发展。",{"$nulls":5},"该项目委托第三方机构为兰州新区化工园区已投产企业开展专业化隐患排查治理，通过全方位的专业化隐患排查治理，有效防范各类安全风险，遏制各类生产安全事故发生，于2024年5月万层指导服务，检查企业89家，出具检查报告90份，提出问题隐患2956项，重大隐患170项，目前已完成整改2336项。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=200万元","200","6.67","万元","100.00%","6.67",""]
[{"$nulls":3},"社会成本指标",null,"提升企业本质安全水平",null,"提升","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态成本指标",null,"预防环境污染",null,"预防","100%-80%(含)","6.66","","100%","5.99",""]
[null,"产出指标",null,"数量指标",null,"检查企业数量",null,">=72家","72","6.67","家","100.00%","6.67",""]
[{"$nulls":5},"问题隐患清单",null,">=72份","72","6.67","份","100.00%","6.67",""]
[{"$nulls":3},"质量指标",null,"奖励企业自动化和安全管理水平",null,"提升","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":5},"隐患合格率",null,">=100%","95","6.67","%","95.00%","6.67",""]
[{"$nulls":3},"时效指标",null,"及时复核企业问题整改情况",null,"及时","100%-80%(含)","6.65","","100%","5.99",""]
[{"$nulls":5},"及时开展隐患排查",null,"及时","100%-80%(含)","6.67","","100%","6",""]
[null,"效益指标",null,"经济效益指标",null,"减少经济损失",null,"减少","100%-80%(含)","10","","100%","9",""]
[{"$nulls":3},"社会效益指标",null,"预防事故发生",null,"预防","100%-80%(含)","10","","100%","9",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"企业满意度",null,">=95%","95","10","%","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"94.66"]

{"sheet":"安全生产标准化评审与危化品建设项目安全审查费用专项资金","index":4,"n_rows":30,"n_cols":14,"rows_kept":30,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,27,0],[16,1,18,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,1,24,2],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,3,22,4],[21,5,21,6],[22,5,22,6],[23,3,24,4],[23,5,23,6],[24,5,24,6],[25,1,26,2],[25,3,25,4],[25,5,25,6],[26,3,26,4],[26,5,26,6],[27,1,27,2],[27,3,27,4],[27,5,27,6],[28,0,28,13],[29,0,29,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"安全生产标准化评审与危化品建设项目安全审查费用专项资金"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"1400000",null,"1400000",null,"252238",null,"10","18.01","1.8"]
[null,null,"其中：财政拨款",null,"1400000",null,"1400000",null,"252238",null,"-","18.01","1.8"]
[null,null,"上年结转资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[null,null,"其他资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,"修订办法滞后，导致支出率过低"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"2024年度创建20家三级标准化企业，其中工贸10家，化工及危险化学品10家。通过标准化创建，推动企业落实安全生产主体责任，建立健全安全生产管理体系，全面管控生产经营活动各环节的安全生产工作，不断提升安全管理水平；组织审查化工园区危险化学品建设项目50个，所有项目审查合法合规。通过对危险化学品项目技术来源、工艺及设施设备的安全可靠性进行审查，杜绝淘汰禁止落后及不符合产业发展要求项目在新区落地，从源头上杜绝化工项目带来安全风险。",{"$nulls":5},"该项目绩效目标为一是创建20家三级标准化 企业，其中工贸10家，化工及危化品行业10家，通过标准化创建，推动企业落实安全生产主体责任，建立健全安全生产管理体系，全面掌控生产经营各各环节的安全生产工作，二是组织审查化工园区危险化学品建设项目50个，通过审查对危化品项目技术来源、工艺及设施设备的安全可靠性进行审查，截止2024年12月底共创建10家三级标准化企业，其中工贸5家，化工及危险化学品5家，组织审查化工园区危险化学品建设项目25个，未完成的主要原因是遴选标准化第三方评审单位及修订安全专家管理办法，致使相关经费未能及时支出。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=140万元","25.22","6.67","万元","100.00%","6.67",""]
[{"$nulls":3},"社会成本指标",null,"降低安全风险，减少经济损失",null,"提升","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态成本指标",null,"预防环境污染",null,"预防","100%-80%(含)","6.66","","100%","5.99",""]
[null,"产出指标",null,"数量指标",null,"三级标准化达标企业数量",null,">=20家","13","6.67","家","65.00%","4.34",""]
[{"$nulls":5},"审查项目数量",null,">=50个","38","6.67","个","76.00%","5.07",""]
[{"$nulls":3},"质量指标",null,"安全审查合规率",null,">=100%","100","6.67","%","100.00%","6.67",""]
[{"$nulls":5},"标准化达标率",null,">=100%","100","6.67","%","100.00%","6.67",""]
[{"$nulls":3},"时效指标",null,"安全审查时间",null,"及时","80%-60%(含)","6.67","","80%","4.67",""]
[{"$nulls":5},"项目成本",null,"<=140万元","25.22","6.65","万元","100.00%","6.65",""]
[null,"效益指标",null,"经济效益指标",null,"提升安全水平，源头降低安全风险",null,"提升","100%-80%(含)","10","","100%","9",""]
[{"$nulls":3},"社会效益指标",null,"减少事故发生",null,"减少","100%-80%(含)","10","","100%","9",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"企业满意度",null,">=95%","95","10","%","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"82.53"]

{"sheet":"应急救援综合能力提升项目","index":5,"n_rows":34,"n_cols":14,"rows_kept":34,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,31,0],[16,1,17,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,1,28,2],[18,3,21,4],[18,5,18,6],[19,5,19,6],[20,5,20,6],[21,5,21,6],[22,3,25,4],[22,5,22,6],[23,5,23,6],[24,5,24,6],[25,5,25,6],[26,3,28,4],[26,5,26,6],[27,5,27,6],[28,5,28,6],[29,1,30,2],[29,3,29,4],[29,5,29,6],[30,3,30,4],[30,5,30,6],[31,1,31,2],[31,3,31,4],[31,5,31,6],[32,0,32,13],[33,0,33,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"应急救援综合能力提升项目"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"2200000",null,"2200000",null,"1482848",null,"10","67.4","6.74"]
[null,null,"其中：财政拨款",null,"2200000",null,"2200000",null,"1482848",null,"-","67.4","6.74"]
[null,null,"上年结转资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[null,null,"其他资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,"项目建设方案滞后"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"更新新区全域地图矢量数据，构建应急指挥一张图，建设融合通信基础软件框架，搭建多部门视频会议控制系统，建设视频管理平台，实现数据信息综合显示、管理和信息交互，建设应急指挥固定电话系统，各部门系统内部运行系统对接接入，分功能场所改建及配套设备。",{"$nulls":5},"该项目于2024年12月在兰州新区科文旅集团大数据中心智慧应急模块建设兰州新区应急智慧中心，更新新区全域地图矢量数据，构建应急智慧一张图，建设融合通信基础软件框架 ，搭建多部门视频会议控制系统，建设视频管理平台，实现数据信息综合显示、管理和信息交互，建设视频管理平台。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=220万元","148.28","10","万元","100.00%","10","项目建设方案滞后"]
[{"$nulls":3},"社会成本指标",null,"提升应急救援协同能力",null,"提升","80%-60%(含)","10","","80%","7","项目建设方案滞后"]
[null,"产出指标",null,"数量指标",null,"构建指挥一张图",null,">=1张","1","3.64","张","100.00%","3.64",""]
[{"$nulls":5},"建设视频会议控制系统",null,">=1套","1","3.64","套","100.00%","3.64",""]
[{"$nulls":5},"建设音视频管理平台",null,">=1套","1","3.64","套","100.00%","3.64",""]
[{"$nulls":5},"应急指挥场所改建",null,">=1处","1","3.64","处","100.00%","3.64",""]
[{"$nulls":3},"质量指标",null,"构建指挥一张图数据准确率",null,">=100%","95","3.64","%","95.00%","3.64",""]
[{"$nulls":5},"建立融合通信系统信息数据共享率",null,">=100%","98","3.64","%","98.00%","3.64",""]
[{"$nulls":5},"建设音视频管理平台，实现应急指挥传递率",null,">=100%","95","3.64","%","95.00%","3.64",""]
[{"$nulls":5},"应急指挥场所改建合格率",null,">=100%","95","3.64","%","95.00%","3.64",""]
[{"$nulls":3},"时效指标",null,"及时更新新区全域地图矢量数据",null,"及时","80%-60%(含)","3.64","","80%","2.55","项目建设方案滞后"]
[{"$nulls":5},"及时开展信息采集",null,"及时","80%-60%(含)","3.64","","80%","2.55","项目建设方案滞后"]
[{"$nulls":5},"及时完善场所硬件设施",null,"及时","80%-60%(含)","3.6","","80%","2.52","项目建设方案滞后"]
[null,"效益指标",null,"经济效益指标",null,"提高应急救援效率和能力，减少损失",null,"减少","100%-80%(含)","10","","100%","9",""]
[{"$nulls":3},"社会效益指标",null,"提高应急救援决策能力",null,"提高","100%-80%(含)","10","","100%","9",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"群众满意度",null,">=95%","95","10","%","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"88.48"]

{"sheet":"气象服务专项经费","index":6,"n_rows":34,"n_cols":14,"rows_kept":34,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,31,0],[16,1,17,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,1,28,2],[18,3,22,4],[18,5,18,6],[19,5,19,6],[20,5,20,6],[21,5,21,6],[22,5,22,6],[23,3,25,4],[23,5,23,6],[24,5,24,6],[25,5,25,6],[26,3,28,4],[26,5,26,6],[27,5,27,6],[28,5,28,6],[29,1,30,2],[29,3,29,4],[29,5,29,6],[30,3,30,4],[30,5,30,6],[31,1,31,2],[31,3,31,4],[31,5,31,6],[32,0,32,13],[33,0,33,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"气象服务专项经费"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"480000",null,"480000",null,"380000",null,"10","79.16","7.91"]
[null,null,"其中：财政拨款",null,"480000",null,"480000",null,"380000",null,"-","79.16","7.91"]
[null,null,"上年结转资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[null,null,"其他资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,"剩余10万元中期调整成气象评估报告尾款"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"提供兰州新区灾害性天气预报预警服务、灾害性天气实况服务、气象信息专报服务以及发送信息的短信服务费、新区气象监测设备维护费等。",{"$nulls":5},"该项目聘请兰州市气象局相关专业技术人员对新区气象监测设备进行定期维护保养，为新区提供气象数据，wield新区气象监测站软件平台升级维护，并为新区提供专业气象服务，包括提供兰州新区灾害性天气预报预警服务、灾害性天气实况服务、气象信息专报服务等，剩余10万元中期调整成气象评估报告尾款。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=48万元","38","10","万元","100.00%","10","剩余10万元中期调整成气象评估报告尾款"]
[{"$nulls":3},"社会成本指标",null,"减轻灾害性天气损失",null,"减轻","100%-80%(含)","10","","100%","9",""]
[null,"产出指标",null,"数量指标",null,"导出气象监测站数据",null,">=13个","13","3.64","个","100.00%","3.64",""]
[{"$nulls":5},"软件平台系统升级维护",null,">=1份","1","3.64","份","100.00%","3.64",""]
[{"$nulls":5},"提供全年灾害性天气预报预警",null,"提供","100%-80%(含)","3.64","","100%","3.28",""]
[{"$nulls":5},"维护气象监测站点设备",null,">=8个","8","3.64","个","100.00%","3.64",""]
[{"$nulls":5},"整理编制年度气象资料",null,">=1份","1","3.64","份","100.00%","3.64",""]
[{"$nulls":3},"质量指标",null,"气象监测站点设备正常运行率",null,">=95%","95","3.64","%","100.00%","3.64",""]
[{"$nulls":5},"气象预报预警信息准确率",null,">=85%","85","3.64","%","100.00%","3.64",""]
[{"$nulls":5},"气象资料数据准确率",null,">=100%","100","3.64","%","100.00%","3.64",""]
[{"$nulls":3},"时效指标",null,"及时发布气象预报预警",null,"及时","100%-80%(含)","3.64","","100%","3.28",""]
[{"$nulls":5},"及时升级软件平台",null,"及时","100%-80%(含)","3.6","","100%","3.24",""]
[{"$nulls":5},"及时维护气象监测设备",null,"及时","100%-80%(含)","3.64","","100%","3.28",""]
[null,"效益指标",null,"社会效益指标",null,"提升气象服务质量",null,"提升","100%-80%(含)","10","","100%","9",""]
[{"$nulls":3},"生态效益指标",null,"提升气象预警服务能力",null,"提升","100%-80%(含)","10","","100%","9",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"提升群众气象服务满意度",null,">=95%","95","10","%","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"93.48"]

{"sheet":"甘肃省自然灾害应急能力提升工程基层防灾项目经费","index":7,"n_rows":29,"n_cols":14,"rows_kept":29,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,26,0],[16,1,18,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,1,22,2],[19,3,19,4],[19,5,19,6],[20,3,21,4],[20,5,20,6],[21,5,21,6],[22,3,22,4],[22,5,22,6],[23,1,25,2],[23,3,23,4],[23,5,23,6],[24,3,24,4],[24,5,24,6],[25,3,25,4],[25,5,25,6],[26,1,26,2],[26,3,26,4],[26,5,26,6],[27,0,27,13],[28,0,28,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘肃省自然灾害应急能力提升工程基层防灾项目经费"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"2074900",null,"2074900",null,"10","100","10"]
[null,null,"其中：财政拨款",null,"null",null,"2074900",null,"2074900",null,"-","100","10"]
[null,null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[null,null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,"已完成"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"全面提升基层防灾能力，降低灾害风险，增强应对能力，确保人民群众的生命安全和财产安全.",{"$nulls":5},"为各乡镇社区配备防汛抗旱、地质灾害应急救援相关设备，提高新区基层灾害处置及应急救援能力，提升响应各类突发灾害事件速度。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=260万元","207.49","6.67","万元","100.00%","6.67",""]
[{"$nulls":3},"社会成本指标",null,"提高应急救援能力，较少事故发生",null,"提高","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态成本指标",null,"减少事故发生，提升新区生态环境整体水平",null,"提升","100%-80%(含)","6.66","","100%","5.99",""]
[null,"产出指标",null,"数量指标",null,"配备乡级救援队伍装备",null,">=8支","8","10","支","100.00%","10",""]
[{"$nulls":3},"质量指标",null,"设备合格率",null,">=100%","100","10","%","100.00%","10",""]
[{"$nulls":5},"装备质量合格率",null,">=100%","100","10","%","100.00%","10",""]
[{"$nulls":3},"时效指标",null,"装备配备及时性",null,"及时","100%-80%(含)","10","","100%","9",""]
[null,"效益指标",null,"经济效益指标",null,"提升灾害应急救援能力",null,"提升","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"社会效益指标",null,"提高应急救援响应速度",null,"提高","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态效益指标",null,"提高社会安全感和稳定性",null,"提升","100%-80%(含)","6.66","","100%","5.99",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"服务群众满意度",null,">=90%","90","10","%","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"95.65"]

{"sheet":"甘肃省自然灾害应急能力提升工程基层防灾项目（本级配套）","index":8,"n_rows":28,"n_cols":14,"rows_kept":28,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,25,0],[16,1,18,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,1,21,2],[19,3,19,4],[19,5,19,6],[20,3,20,4],[20,5,20,6],[21,3,21,4],[21,5,21,6],[22,1,24,2],[22,3,22,4],[22,5,22,6],[23,3,23,4],[23,5,23,6],[24,3,24,4],[24,5,24,6],[25,1,25,2],[25,3,25,4],[25,5,25,6],[26,0,26,13],[27,0,27,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘肃省自然灾害应急能力提升工程基层防灾项目（本级配套）"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"66000",null,"65884.1",null,"10","99.82","9.98"]
[null,null,"其中：财政拨款",null,"null",null,"66000",null,"65884.1",null,"-","99.82","9.98"]
[null,null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[null,null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"完成兰州新区基层应急救援队伍装备配备，切实提升基层应急力量快速响应和先期处置能力以及基层抢险救援和自救互救能力显著增强。",{"$nulls":5},"为各乡镇社区配备防汛抗旱、地质灾害应急救援相关设备，提高新区基层灾害处置及应急救援能力，提升响应各类突发灾害事件速度。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=6.6万元","6.59","6.67","万元","100.00%","6.67",""]
[{"$nulls":3},"社会成本指标",null,"提高新区整体应急能力水平",null,"提高","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态成本指标",null,"减少环境污染",null,"减少","100%-80%(含)","6.66","","100%","5.99",""]
[null,"产出指标",null,"数量指标",null,"完成8支基层救援队装备配备",null,">=95个","95","13.33","个","100.00%","13.33",""]
[{"$nulls":3},"质量指标",null,"基层救援队装备配备合格率",null,">=95%","95","13.33","%","100.00%","13.33",""]
[{"$nulls":3},"时效指标",null,"按期完成装备采购",null,">=100%","100","13.34","%","100.00%","13.34",""]
[null,"效益指标",null,"经济效益指标",null,"提高应急救援响应速度",null,">=95%","93","6.67","%","97.89%","6.67",""]
[{"$nulls":3},"社会效益指标",null,"提升自救互救能力",null,"提高","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态效益指标",null,"提高新区整体生态环境水平",null,"提高","100%-80%(含)","6.66","","100%","5.99",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"群众满意度",null,">=95%","","10","%","","0",""]
[]
["总分",{"$nulls":8},100,null,null,"87.3"]

{"sheet":"”陇原砺剑.2023“演习","index":9,"n_rows":30,"n_cols":14,"rows_kept":30,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,27,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,23,2],[17,3,19,4],[17,5,17,6],[18,5,18,6],[19,5,19,6],[20,3,21,4],[20,5,20,6],[21,5,21,6],[22,3,23,4],[22,5,22,6],[23,5,23,6],[24,1,26,2],[24,3,24,4],[24,5,24,6],[25,3,25,4],[25,5,25,6],[26,3,26,4],[26,5,26,6],[27,1,27,2],[27,3,27,4],[27,5,27,6],[28,0,28,13],[29,0,29,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"”陇原砺剑.2023“演习"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"6450000",null,"5999789",null,"10","93.01","9.3"]
[null,null,"其中：财政拨款",null,"null",null,"0",null,"0",null,"-","0","0"]
[null,null,"上年结转资金",null,"null",null,"6450000",null,"5999789",null,"-","93.01","9.3"]
[null,null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,"已完成"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"按照部省演习构想和科目要求，倒排工期，挂图作战，强力推动主演习场所、设施的搭建，参演期间物资、通讯、燃油料、运输工具和设施设备装备购置等工作，全力确保演习场如期完工并交付使用。",{"$nulls":5},"该项目为2023年度甘肃省应急厅举办的“陇原砺剑.2023”抗震救灾实战演习活动，该项目于2023年5月演习，此次演习得到了省委、省政府两道的肯定，得到了社会各界的认可，演习全面检验了应急智慧体系、应急预案体系、应急力量体系、智慧协调机制、抢险救援能力和基层应急能力。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=成本控制率万元","100%-80%(含)","20","万元","100%","18",""]
[null,"产出指标",null,"数量指标",null,"顶板混凝土砌筑",null,"顶板混凝土砌筑","100%-80%(含)","5.71","","100%","5.14",""]
[{"$nulls":5},"模拟集贸市场轻钢结构安装 ",null,"模拟集贸市场轻钢结构安装 ","100%-80%(含)","5.71","","100%","5.14",""]
[{"$nulls":5},"模拟建筑物配套设施",null," 模拟建筑物配套设施","100%-80%(含)","5.71","","100%","5.14",""]
[{"$nulls":3},"质量指标",null,"建筑物配套设施合格率",null,">=建筑物配套设施合格率%","100%-80%(含)","5.71","%","100%","5.14",""]
[{"$nulls":5},"模拟建筑物质量合格率",null,">=建筑物配套设施合格率%","100%-80%(含)","5.71","%","100%","5.14",""]
[{"$nulls":3},"时效指标",null,"模拟建筑主体建造完成",null,"模拟建筑主体建造完成","100%-80%(含)","5.74","","100%","5.17",""]
[{"$nulls":5},"完成建筑物配套水电设施",null,"模拟建筑主体建造完成","100%-80%(含)","5.71","","100%","5.14",""]
[null,"效益指标",null,"经济效益指标",null,"各类机制得到全面运用",null,"各类机制得到全面运用","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"社会效益指标",null,"防震减灾氛围",null,"防震减灾氛围","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态效益指标",null,"群众防灾减灾意识",null,"群众防灾减灾意识","100%-80%(含)","6.66","","100%","5.99",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"群众满意度",null,">=群众满意度%","100%-80%(含)","10","%","100%","9",""]
[]
["总分",{"$nulls":8},100,null,null,"90.3"]

{"sheet":"2023年安全生产及应急专项","index":10,"n_rows":35,"n_cols":14,"rows_kept":35,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,32,0],[16,1,18,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,1,27,2],[19,3,21,4],[19,5,19,6],[20,5,20,6],[21,5,21,6],[22,3,24,4],[22,5,22,6],[23,5,23,6],[24,5,24,6],[25,3,27,4],[25,5,25,6],[26,5,26,6],[27,5,27,6],[28,1,31,2],[28,3,29,4],[28,5,28,6],[29,5,29,6],[30,3,31,4],[30,5,30,6],[31,5,31,6],[32,1,32,2],[32,3,32,4],[32,5,32,6],[33,0,33,13],[34,0,34,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"2023年安全生产及应急专项"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"1400000",null,"1361500",null,"10","97.25","9.72"]
[null,null,"其中：财政拨款",null,"null",null,"0",null,"0",null,"-","0","0"]
[null,null,"上年结转资金",null,"null",null,"1400000",null,"1361500",null,"-","97.25","9.72"]
[null,null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,"已完成"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"由社区组织开展创建工作。进一步增强社区居民防灾减灾意识，普及预防、避险、自救、互救等应急防护知识，提高社区应对各种突发性灾害的快速反应和救助能力。积极防范化解各类安全风险。围绕地质灾害、气象灾害、水旱灾害、地震等新区易发多发自然灾害信息，结合已有自然灾害风险普查和隐患排查的重大风险与隐患区域，加快推进自然灾害风险监测预警感知网络、监控网络建设，构建一个以普查为起点的闭环业务全景图，借力兰州新区新型智慧城市项目平台开发应急板块，以自然灾害综合风险数据为依托，围绕事前预防预警、事中应急救援、事后调查评估全链条开展普查成果本地化应用，借助信息化手段达成应急管理业务的一体化管理。",{"$nulls":5},"该预算分为灾害普查成果应用和化工园区应急救援装备配备项目，灾害普查成果应用项目委托兰州新区大数据投资建设管理有限公司开展建设，该项目利用智慧城市及政务信息化建设成果数据库，汇聚自然灾害风险普查成果数据相关的数据资源，建设了普查成果数据和应用平台。化工园区应急救援装备配备项目由化工园区管委会采购配备救援装备，已完成采购。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"经济成本控制率",null,"经济成本控制率","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"社会成本指标",null,"成本控制率",null,"成本控制率","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态成本指标",null,"生态环境成本控制率",null,"生态环境成本控制率","100%-80%(含)","6.66","","100%","5.99",""]
[null,"产出指标",null,"数量指标",null,"按照定额标准采购急需的应急救援装备",null,"按照定额标准采购急需的应急救援装备","100%-80%(含)","4.44","","100%","4",""]
[{"$nulls":5},"兰州新区自然灾害综合监测预警系统",null,"兰州新区自然灾害综合监测预警系统","100%-80%(含)","4.44","","100%","4",""]
[{"$nulls":5},"完成3个省级综合减灾示范社区创建",null,"完成3个省级综合减灾示范社区创建","100%-80%(含)","4.44","","100%","4",""]
[{"$nulls":3},"质量指标",null,"采购装备质量达标率",null,"采购装备质量达标率","100%-80%(含)","4.44","","100%","4",""]
[{"$nulls":5},"创建社区达标率",null,"创建社区达标率","100%-80%(含)","4.44","","100%","4",""]
[{"$nulls":5},"监测预警系统达标率",null,"监测预警系统达标率","100%-80%(含)","4.44","","100%","4",""]
[{"$nulls":3},"时效指标",null,"采购及配备及时性",null,"采购及配备及时性","100%-80%(含)","4.44","","100%","4",""]
[{"$nulls":5},"及时完成系统建设运用",null,"及时完成系统建设运用","100%-80%(含)","4.44","","100%","4",""]
[{"$nulls":5},"应急演练达标率",null,"应急演练达标率","80%-60%(含)","4.48","","80%","3.14",""]
[null,"效益指标",null,"经济效益指标",null,"提升灾害应急救援能力",null,"提升灾害应急救援能力","100%-80%(含)","5","","100%","4.5",""]
[{"$nulls":5},"应急救援能力显著提升",null,"应急救援能力显著提升","100%-80%(含)","5","","100%","4.5",""]
[{"$nulls":3},"社会效益指标",null,"提高应对各种突发性灾害救助",null,"积极防范化解各类安全风险","100%-80%(含)","5","","100%","4.5",""]
[{"$nulls":5},"协调联动和应急能力处置",null,"协调联动和应急能力处置","100%-80%(含)","5","","100%","4.5",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"群众满意度",null,"群众满意度","100%-80%(含)","10","","100%","9",""]
[]
["总分",{"$nulls":8},100,null,null,"89.86"]

{"sheet":"危险化学品安全知识竞赛及化工园区安全技能实训基地宣传推广补助资","index":11,"n_rows":29,"n_cols":14,"rows_kept":29,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,26,0],[16,1,18,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,1,22,2],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,3,21,4],[21,5,21,6],[22,3,22,4],[22,5,22,6],[23,1,25,2],[23,3,23,4],[23,5,23,6],[24,3,24,4],[24,5,24,6],[25,3,25,4],[25,5,25,6],[26,1,26,2],[26,3,26,4],[26,5,26,6],[27,0,27,13],[28,0,28,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"危险化学品安全知识竞赛及化工园区安全技能实训基地宣传推广补助资金"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"110000",null,"110000",null,"110000",null,"10","100","10"]
[null,null,"其中：财政拨款",null,"110000",null,"110000",null,"110000",null,"-","100","10"]
[null,null,"上年结转资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[null,null,"其他资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,"已完成"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"承办全国危险化学品安全知识竞赛西部地区复赛，提高危险化学品从业人员安全意识和安全知识水平，营造企业自觉落实安全生产主体责任的良好氛围。",{"$nulls":5},"举办兰州新区安全知识竞赛及化工园区安全技能实训基地宣传活动，该活动提高了危险化学品从业人员安全意识和安全知识水平，营造了企业自觉落实安全生产主体责任的良好氛围，另一方面在中国化工报等新闻媒体及微信公众号专题做了报道，对新区化工园区和安全技能实训基地起到了很好的宣传作用。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"预防事故发生，减少经济损失。",null,"减少","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"社会成本指标",null,"提高安全意识和知识水平",null,"提高","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态成本指标",null,"预防环境污染",null,"预防","100%-80%(含)","6.66","","100%","5.99",""]
[null,"产出指标",null,"数量指标",null,"承办安全知识竞赛次数",null,">=1次","1","10","次","100.00%","10",""]
[{"$nulls":5},"推介宣传次数",null,">=2次","2","10","次","100.00%","10",""]
[{"$nulls":3},"质量指标",null,"举办知识竞赛合格率",null,">=90%","90","10","%","100.00%","10",""]
[{"$nulls":3},"时效指标",null,"按期完成知识竞赛",null,"按期","100%-80%(含)","10","","100%","9",""]
[null,"效益指标",null,"经济效益指标",null,"减少经济损失",null,"减少","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"社会效益指标",null,"提升安全知识水平",null,"提升","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态效益指标",null,"防治环境污染",null,"预防","100%-80%(含)","6.66","","100%","5.99",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"企业满意度",null,">=90%","90","10","%","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"94.98"]

{"sheet":"公共安全监管能力提升项目","index":12,"n_rows":31,"n_cols":14,"rows_kept":31,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,28,0],[16,1,17,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,1,24,2],[18,3,20,4],[18,5,18,6],[19,5,19,6],[20,5,20,6],[21,3,22,4],[21,5,21,6],[22,5,22,6],[23,3,24,4],[23,5,23,6],[24,5,24,6],[25,1,27,2],[25,3,25,4],[25,5,25,6],[26,3,26,4],[26,5,26,6],[27,3,27,4],[27,5,27,6],[28,1,28,2],[28,3,28,4],[28,5,28,6],[29,0,29,13],[30,0,30,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"公共安全监管能力提升项目"]
["主管部门",null,"兰州新区应急管理局",{"$nulls":5},"实施单位",null,"兰州新区应急管理局"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"100000",null,"100000",null,"0",null,"10","0","0"]
[null,null,"其中：财政拨款",null,"100000",null,"100000",null,"null",null,"-","0","0"]
[null,null,"上年结转资金",null,"0",null,"0",null,"null",null,"-","0","0"]
[null,null,"其他资金",null,"0",null,"0",null,"null",null,"-","0","0"]
[]
["未完成原因分析",null,"防火期一月份开始"]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"开展森林草原防灭火一线扑火人员和指挥人员培训教育，购置森林草原防火新装备，开发新技术应用，对防灭火机具的操作使用和维修保养技能进行培训。",{"$nulls":5},"根据2024年实际情况，我局于12月开展森林草原防灭火设备购置及人员培训，但因防火期延长到2月份，导致支出进度滞后"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"节约培训成本",null,"<=150元","0","10","元","100.00%","10","因防火期延长到2月份，导致支出进度滞后."]
[{"$nulls":3},"社会成本指标",null,"减少火灾发生率",null,"减少","100%-80%(含)","10","","100%","9",""]
[null,"产出指标",null,"数量指标",null,"更新设备数量",null,">=50套","50","5.71","套","100.00%","5.71",""]
[{"$nulls":5},"举办培训班次数",null,">=1次","1","5.71","次","100.00%","5.71",""]
[{"$nulls":5},"培训指挥人员",null,">=200人","200","5.71","人","100.00%","5.71",""]
[{"$nulls":3},"质量指标",null,"购买设备合格率",null,">=100%","100","5.71","%","100.00%","5.71",""]
[{"$nulls":5},"培训合格率",null,">=98%","98","5.71","%","100.00%","5.71",""]
[{"$nulls":3},"时效指标",null,"及时购置新设备",null,"及时","80%-60%(含)","5.71","","80%","4","因防火期延长到2月份，导致支出进度滞后."]
[{"$nulls":5},"及时在防火期前开展人员培训",null,"及时","80%-60%(含)","5.74","","80%","4.02","因防火期延长到2月份，导致支出进度滞后."]
[null,"效益指标",null,"经济效益指标",null,"减少森林草原火灾发生率",null,"减少","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"社会效益指标",null,"减少火灾经济损失",null,"减少","100%-80%(含)","6.67","","100%","6",""]
[{"$nulls":3},"生态效益指标",null,"减少森林草原破坏率",null,"减少","100%-80%(含)","6.66","","100%","5.99",""]
[null,"满意度指标",null,"服务对象满意度指标",null,"参训人员满意率",null,">=90%","90","10","%","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"83.56"]