{"text_format":"3","workbook":"xlsx","n_sheets":23,"sheets":["2024年省政府为民办实事妇女“两癌”筛查项目（省级）","甘财社【2023】2号2022年中央转移支付医疗服务于保障能力","2024年中央转移支付医疗服务与保障能力提升（中医药事业传承与","2024年基本公共卫生服务补助资金预算（省级）","2024年中央财政医疗服务与保障能力提升（公立医院综合改革）补","2024年医疗服务与保障能力提升（医疗卫生机构能力建设、卫生健","2024年中央财政重大传染病防控项目资金（中央）","2024年省级中医药专项补助资金","2024年县级公立医院取消药品加成省级补助资金","2024年第二批基本公共卫生服务补助资金（省级）","2024年医疗服务与保障能力提升（公立医院综合改革）第二批补助","2024年重大公共卫生服务补助资金（中央）","2024年急救运转经费（本级）","2024年医师节护士节活动经费（本级）","2024年急救运转经费","2024年兰州新区健康中国中医药专项活动资金（本级）","2024年省政府为民办实事妇女“两癌”筛查项目-妇女两癌筛查经","2024年医政医改管理经费","妇幼安全保障经费（本级）","数据中心卫生专网费用（本级）","新区托育机构配套补助资金（本级）","医养结合工作经费（本级）","业务用房租赁费（占比70）（第一人民医院）"],"read":"whole","date_system":"1900"}

{"sheet":"2024年省政府为民办实事妇女“两癌”筛查项目（省级）","index":0,"n_rows":25,"n_cols":14,"rows_kept":25,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,22,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,19,2],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,3,19,4],[19,5,19,6],[20,1,21,2],[20,3,21,4],[20,5,20,6],[21,5,21,6],[22,1,22,2],[22,3,22,4],[22,5,22,6],[23,0,23,13],[24,0,24,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财行〔2024〕8号-兰州新区第一人民医院-2024年省政府为民办实事妇女“两癌”筛查项目（省级）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"66000",null,"66000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"66000",null,"66000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"逐步提高新区广大育龄妇女自觉参与两癌检查的意识，确保项目检查目标人群覆盖率，增强新区妇女保健意识，提升妇女健康保障水平，促进经济社会和谐发展。",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=100百分数","100","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"妇女两癌检查人数",null,">=1100人","1100","13.33","人","100.00%","13.33",""]
["绩效目标","产出指标",null,"质量指标",null,"两癌检查完成率",null,">=100百分数","100","13.33","百分数","100.00%","13.33",""]
["绩效目标","产出指标",null,"时效指标",null,"资金到位率",null,">=100百分数","100","13.34","百分数","100.00%","13.34",""]
["绩效目标","效益指标",null,"社会效益指标",null,"妇女“两癌”防治知晓率和自我保健意识",null,"逐步提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"减少出生缺陷发生，不断提高出生人口素质",null,"逐步提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"服务对象满意度",null,">=80百分数","80","10","百分数","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"98"]

{"sheet":"甘财社【2023】2号2022年中央转移支付医疗服务于保障能力","index":1,"n_rows":26,"n_cols":14,"rows_kept":26,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,23,0],[16,1,17,2],[16,3,16,4],[16,5,16,6],[17,3,17,4],[17,5,17,6],[18,1,20,2],[18,3,18,4],[18,5,18,6],[19,3,19,4],[19,5,19,6],[20,3,20,4],[20,5,20,6],[21,1,22,2],[21,3,21,4],[21,5,21,6],[22,3,22,4],[22,5,22,6],[23,1,23,2],[23,3,23,4],[23,5,23,6],[24,0,24,13],[25,0,25,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财社【2023】2号2022年中央转移支付医疗服务于保障能力提升（医疗卫生机构能力建设）补助资金（第二批）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"7491281",null,"7491281",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"7491281",null,"7491281",null,"-","100","10"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"根据上级政策，支持我院临床临床重点专科建设，提高医疗服务能力建设及承担疫情重点救治任务医院能力建设，加强疫情救治相关设备配置，强化疫情救助人才培训，加强医防融合，提升疫情防治能力。",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=90%","90","10","%","100.00%","10",""]
["绩效目标","成本指标",null,"社会成本指标",null,"医院综合服务率",null,"有效提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","产出指标",null,"数量指标",null,"智能化一体平台",null,"=1套","1","13.33","套","100.00%","13.33",""]
["绩效目标","产出指标",null,"质量指标",null,"购置资金使用率",null,"=100%","100","13.33","%","100.00%","13.33",""]
["绩效目标","产出指标",null,"时效指标",null,"资金支付及时性",null,"及时","100%-80%(含)","13.34","","100%","12.01",""]
["绩效目标","效益指标",null,"经济效益指标",null,"控制疫情救助成本",null,"良好","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"应对疫情与突发事件能力",null,"较上一年提高","100%-80%(含)","10","","100%","9",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"医院医务人员及患者满意",null,">=90%","90","10","%","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"95.67"]

{"sheet":"2024年中央转移支付医疗服务与保障能力提升（中医药事业传承与","index":2,"n_rows":29,"n_cols":14,"rows_kept":29,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,26,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,22,2],[17,3,18,4],[17,5,17,6],[18,5,18,6],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,3,22,4],[21,5,21,6],[22,5,22,6],[23,1,24,2],[23,3,23,4],[23,5,23,6],[24,3,24,4],[24,5,24,6],[25,1,26,2],[25,3,26,4],[25,5,25,6],[26,5,26,6],[27,0,27,13],[28,0,28,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财社〔2023〕153号-兰州新区第一人民医院-2024年中央转移支付医疗服务与保障能力提升（中医药事业传承与发展部分）补助项目（中央）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"100000",null,"100000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"100000",null,"100000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"为大力发展新区中医药事业，根据省财政厅、省卫生健康委员会《关于提前下达2024年中央转移支付医疗服务与保障能力提升(中医药事业传承与发展部分)补助资金预算的通知》(甘财社〔2023〕153号)，新区卫生健康委员会《关于印发〈2024年兰州新区健康中国中医药专项活动项目实施方案〉的通知》(新卫函〔2024〕45号)要求，医院主要有以下目标：1.进一步健全中医药服务体系，持续提升中医药服务水平，提高张西医结合服务水平，提高中药重点科室建设水平。2.开展中医药健康宣教、中医馆和中医重点科室服务能力提升等工作。3.打造1家“旗舰中医馆”和10家“旗舰中医阁”。",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=95百分数","95","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"项目经费拨付完成率",null,"=100百分数","100","6.67","百分数","100.00%","6.67",""]
["绩效目标","产出指标",null,"数量指标",null,"中医药服务能力提升",null,">=95百分数","95","6.67","百分数","100.00%","6.67",""]
["绩效目标","产出指标",null,"质量指标",null,"经费保障",null,"=100百分数","100","6.67","百分数","100.00%","6.67",""]
["绩效目标","产出指标",null,"质量指标",null,"中医药服务能力",null,"有效提升","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"时效指标",null,"经费拨付及时性",null,"及时","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"时效指标",null,"中医能力提升及时性",null,"及时","100%-80%(含)","6.65","","100%","5.98",""]
["绩效目标","效益指标",null,"经济效益指标",null,"中医药收入",null,"有效提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"中医治愈率",null,"显著提高","100%-80%(含)","10","","100%","9",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"医疗机构满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
[]
["总分",{"$nulls":8},100,null,null,"95.99"]

{"sheet":"2024年基本公共卫生服务补助资金预算（省级）","index":3,"n_rows":28,"n_cols":14,"rows_kept":28,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,25,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,22,2],[17,3,19,4],[17,5,17,6],[18,5,18,6],[19,5,19,6],[20,3,20,4],[20,5,20,6],[21,3,22,4],[21,5,21,6],[22,5,22,6],[23,1,24,2],[23,3,24,4],[23,5,23,6],[24,5,24,6],[25,1,25,2],[25,3,25,4],[25,5,25,6],[26,0,26,13],[27,0,27,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财社〔2023〕154号-兰州新区第一人民医院-2024年基本公共卫生服务补助资金预算（省级）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"41700",null,"41700",null,"41700",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"41700",null,"41700",null,"41700",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"0",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"通过实施农村妇女两癌检查、贫困地区新生儿疾病筛查、国家免费孕前优生健康检查项目，逐步提高新区农村妇女自我保健意识和广大育龄夫妇自觉参与国家免费孕前优生健康检查的意识，提高“两癌”早诊率，实现早诊早治的目标，降低新生儿遗传代谢病致畸率，确保项目检查目标人群覆盖率，减少出生缺陷发生，不断提高出生人口素质",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"有效保障医院相关支出",null,"有效保障","100%-80%(含)","20","","100%","18",""]
["绩效目标","产出指标",null,"数量指标",null,"“两癌”检测目标人数",null,"=200人","200","6.67","人","100.00%","6.67",""]
["绩效目标","产出指标",null,"数量指标",null,"新生儿筛查人数",null,"=100人","100","6.67","人","100.00%","6.67",""]
["绩效目标","产出指标",null,"数量指标",null,"孕前优生检查人数",null,"=60对","60","6.67","对","100.00%","6.67",""]
["绩效目标","产出指标",null,"质量指标",null,"工作完成质量",null,"=100百分数","100","6.67","百分数","100.00%","6.67",""]
["绩效目标","产出指标",null,"时效指标",null,"项目开展时间",null,"2024年全年","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"时效指标",null,"资金到位率",null,"=100百分数","100","6.65","百分数","100.00%","6.65",""]
["绩效目标","效益指标",null,"社会效益指标",null,"减少出生缺陷发生，出生人口素质有效提高",null,"有效提高","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"农村妇女保健意识",null,"逐步提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"服务对象满意度",null,">=90百分数","90","10","百分数","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"95.33"]

{"sheet":"2024年中央财政医疗服务与保障能力提升（公立医院综合改革）补","index":4,"n_rows":33,"n_cols":14,"rows_kept":33,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,30,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,25,2],[17,3,19,4],[17,5,17,6],[18,5,18,6],[19,5,19,6],[20,3,22,4],[20,5,20,6],[21,5,21,6],[22,5,22,6],[23,3,25,4],[23,5,23,6],[24,5,24,6],[25,5,25,6],[26,1,28,2],[26,3,27,4],[26,5,26,6],[27,5,27,6],[28,3,28,4],[28,5,28,6],[29,1,30,2],[29,3,30,4],[29,5,29,6],[30,5,30,6],[31,0,31,13],[32,0,32,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财社〔2023〕157号-兰州新区第一人民医院-2024年中央财政医疗服务与保障能力提升（公立医院综合改革）补助资金预算"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"1500000",null,"1500000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"1500000",null,"1500000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"持续深化医药卫生体制改革，全面推广紧密型县域医共体工作实际，以“保基本、强基层、建机制”为目标，建立一个责任、管理、服务、利益“四位一体”的紧密型县域医共体，推动优质医疗卫生资源下沉，让老百姓在家门口就近享受二级医院质优价廉的医疗服务",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=90百分数","90","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"“三医联动”一体化监管平台",null,"=1个","1","4.44","个","100.00%","4.44",""]
["绩效目标","产出指标",null,"数量指标",null,"拨付经费完成率",null,"=100百分数","100","4.44","百分数","100.00%","4.44",""]
["绩效目标","产出指标",null,"数量指标",null,"医疗协同平台",null,"=1个","1","4.44","个","100.00%","4.44",""]
["绩效目标","产出指标",null,"质量指标",null,"“三医联动”一体化监管平台达标率",null,"=100百分数","100","4.44","百分数","100.00%","4.44",""]
["绩效目标","产出指标",null,"质量指标",null,"医疗协同平台达标率",null,"=100百分数","100","4.44","百分数","100.00%","4.44",""]
["绩效目标","产出指标",null,"质量指标",null,"足额拨付经费",null,"足额","100%-80%(含)","4.44","","100%","4",""]
["绩效目标","产出指标",null,"时效指标",null,"“三医联动”一体化监管平台建设及时性",null,"及时","100%-80%(含)","4.44","","100%","4",""]
["绩效目标","产出指标",null,"时效指标",null,"经费到账时间",null,"及时","100%-80%(含)","4.48","","100%","4.03",""]
["绩效目标","产出指标",null,"时效指标",null,"医疗协同平台建设及时性",null,"及时","100%-80%(含)","4.44","","100%","4",""]
["绩效目标","效益指标",null,"经济效益指标",null,"加强医疗机构监管",null,"加强","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","效益指标",null,"经济效益指标",null,"推动优质医疗卫生资源下沉",null,"推动","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","效益指标",null,"社会效益指标",null,"让老百姓在家门口就近享受县级以上质优价廉医疗服务",null,"可持续影响","100%-80%(含)","6.66","","100%","5.99",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"群众满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"医疗机构满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
[]
["总分",{"$nulls":8},100,null,null,"96.22"]

{"sheet":"2024年医疗服务与保障能力提升（医疗卫生机构能力建设、卫生健","index":5,"n_rows":27,"n_cols":14,"rows_kept":27,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,24,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,21,2],[17,3,18,4],[17,5,17,6],[18,5,18,6],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,3,21,4],[21,5,21,6],[22,1,23,2],[22,3,23,4],[22,5,22,6],[23,5,23,6],[24,1,24,2],[24,3,24,4],[24,5,24,6],[25,0,25,13],[26,0,26,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财社〔2023〕160号-兰州新区第一人民医院-2024年医疗服务与保障能力提升（医疗卫生机构能力建设、卫生健康人才培养）中央补助资金预算（中央）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"400000",null,"272000",null,"10","68","6.8"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"400000",null,"272000",null,"-","68","6.8"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"1.部署国家传染病监测预警前置软件，实现医疗机构传染病源头数据统一采集、自动采集。\r\n2.提升新区网络安全防护和视频会商能力。",{"$nulls":5},"项目资金支付68%，项目目标基本实现，计划采购的信息软件流程尚未审核完成。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=90百分数","90","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"购置国家传染病智能监测预警前置软件",null,"=1套","1","8","套","100.00%","8",""]
["绩效目标","产出指标",null,"数量指标",null,"相关人才培训 ",null,">=90百分数","90","8","百分数","100.00%","8",""]
["绩效目标","产出指标",null,"质量指标",null,"技术升级和业务保障能力提升",null,"逐步提升","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","产出指标",null,"质量指标",null,"市级疾控部门视频会商系统全覆盖",null,"=100百分数","100","8","百分数","100.00%","8",""]
["绩效目标","产出指标",null,"时效指标",null,"及时部署前置软件",null,"及时","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","效益指标",null,"社会效益指标",null,"升级传染病疫情报告网络安全防护条件",null,"完成升级","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"提升智慧化监测预警和风险评估能力水平",null,"有限提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"监测预警培训学校学员满意度",null,">=90百分数","90","10","百分数","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"93.2"]

{"sheet":"2024年中央财政重大传染病防控项目资金（中央）","index":6,"n_rows":30,"n_cols":14,"rows_kept":30,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,27,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,24,2],[17,3,20,4],[17,5,17,6],[18,5,18,6],[19,5,19,6],[20,5,20,6],[21,3,23,4],[21,5,21,6],[22,5,22,6],[23,5,23,6],[24,3,24,4],[24,5,24,6],[25,1,25,2],[25,3,25,4],[25,5,25,6],[26,1,27,2],[26,3,27,4],[26,5,26,6],[27,5,27,6],[28,0,28,13],[29,0,29,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财社〔2023〕161号-兰州新区第一人民医院-2024年中央财政重大传染病防控项目资金（中央）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"1485900",null,"1485900",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"1485900",null,"1485900",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"1.积极应对艾滋病带来的挑战，最大限度扩大艾滋病病毒抗体筛查，及早发现病毒感染者和病人，有效控制传播，持续减少性传播、输血传播和母婴传播，进一步降低病死率，逐步提高感染者和病人生存质量。2.全面规范落实预防母婴传播综合干预服务，减少相关疾病母婴传播，不断提升妇女儿童健康水平和生活质量。3.加强肺结核患者发现工作，规范治疗和随访检查的患者数不低于任务数的85%，患者的成功治疗率不低于",{"$nulls":5},"按照上级文件要求，资金已全部支付完毕。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=90百分数","90","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"采购病毒载量仪",null,"=1套","1","5","套","100.00%","5",""]
["绩效目标","产出指标",null,"数量指标",null,"采购流式细胞仪",null,"=1套","1","5","套","100.00%","5",""]
["绩效目标","产出指标",null,"数量指标",null,"年度开展培训、督查和技术指导",null,"=4次","4","5","次","100.00%","5",""]
["绩效目标","产出指标",null,"数量指标",null,"孕产妇艾滋病、病毒和乙肝检测率",null,">=95百分数","95","5","百分数","100.00%","5",""]
["绩效目标","产出指标",null,"质量指标",null,"采购设备合格率",null,">=100百分数","100","5","百分数","100.00%","5",""]
["绩效目标","产出指标",null,"质量指标",null,"采样送检质量",null,"合格","100%-80%(含)","5","","100%","4.5",""]
["绩效目标","产出指标",null,"质量指标",null,"规范管理率",null,">=80百分数","80","5","百分数","100.00%","5",""]
["绩效目标","产出指标",null,"时效指标",null,"及时完成病例报告",null,"及时","100%-80%(含)","5","","100%","4.5",""]
["绩效目标","效益指标",null,"社会效益指标",null,"降低结核病感染率、发病率和死亡率",null,"降低","100%-80%(含)","20","","100%","18",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"医疗机构工作人员满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
[]
["总分",{"$nulls":8},100,null,null,"97"]

{"sheet":"2024年省级中医药专项补助资金","index":7,"n_rows":28,"n_cols":14,"rows_kept":28,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,25,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,22,2],[17,3,19,4],[17,5,17,6],[18,5,18,6],[19,5,19,6],[20,3,20,4],[20,5,20,6],[21,3,22,4],[21,5,21,6],[22,5,22,6],[23,1,24,2],[23,3,23,4],[23,5,23,6],[24,3,24,4],[24,5,24,6],[25,1,25,2],[25,3,25,4],[25,5,25,6],[26,0,26,13],[27,0,27,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财社〔2023〕168号-兰州新区第一人民医院-2024年省级中医药专项补助资金"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"630000",null,"628947.6",null,"10","99.83","9.98"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"630000",null,"628947.6",null,"-","99.83","9.98"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"1.建设1个省级中医特色优势专科\r\n2.开展1个省级中医药科研课题",{"$nulls":5},"项目资金支付99.83%，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=90百分数","90","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"建设省级中医特色优势专科",null,"=1个","1","6.67","个","100.00%","6.67",""]
["绩效目标","产出指标",null,"数量指标",null,"开展省级中医药科研课题",null,"=1个","1","6.67","个","100.00%","6.67",""]
["绩效目标","产出指标",null,"数量指标",null,"足额拨付经费",null,"足额","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"质量指标",null,"医院中医治疗能力",null,"有效提升","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"时效指标",null,"经费拨付及时性",null,"及时","100%-80%(含)","6.65","","100%","5.98",""]
["绩效目标","产出指标",null,"时效指标",null,"项目实施周期",null,"<=1年","1","6.67","年","100.00%","6.67",""]
["绩效目标","效益指标",null,"经济效益指标",null,"医院中医药收入",null,"增加","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"提升中医药服务能力‘发挥中医药在维护保障人民群众健康中独特优势和作用’",null,"有效提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90百分数","90","10","百分数","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"95.97"]

{"sheet":"2024年县级公立医院取消药品加成省级补助资金","index":8,"n_rows":28,"n_cols":14,"rows_kept":28,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,25,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,21,2],[17,3,18,4],[17,5,17,6],[18,5,18,6],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,3,21,4],[21,5,21,6],[22,1,24,2],[22,3,24,4],[22,5,22,6],[23,5,23,6],[24,5,24,6],[25,1,25,2],[25,3,25,4],[25,5,25,6],[26,0,26,13],[27,0,27,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财社〔2023〕168号-兰州新区第一人民医院-2024年县级公立医院取消药品加成省级补助资金"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"990000",null,"990000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"990000",null,"990000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"县级医院医疗服务能力得到提升",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=90百分数","90","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"带量采购药品数",null,"最大化","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","产出指标",null,"数量指标",null,"取消药品加成的药品数",null,"全部西药，全部中成药","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","产出指标",null,"质量指标",null,"工作考核合格率",null,">=85百分数","85","8","百分数","100.00%","8",""]
["绩效目标","产出指标",null,"质量指标",null,"县级公立医院基本药物价格",null,"降低","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","产出指标",null,"时效指标",null,"资金支付及时性",null,"及时","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","效益指标",null,"社会效益指标",null,"基层群众看病难、看病贵问题",null,"缓解","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","效益指标",null,"社会效益指标",null,"群众用药经济负担",null,"降低","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","效益指标",null,"社会效益指标",null,"县级公立医院服务能力",null,"提升","100%-80%(含)","6.66","","100%","5.99",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90百分数","90","10","百分数","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"94.79"]

{"sheet":"2024年第二批基本公共卫生服务补助资金（省级）","index":9,"n_rows":28,"n_cols":14,"rows_kept":28,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,25,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,19,2],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,3,19,4],[19,5,19,6],[20,1,23,2],[20,3,23,4],[20,5,20,6],[21,5,21,6],[22,5,22,6],[23,5,23,6],[24,1,25,2],[24,3,25,4],[24,5,24,6],[25,5,25,6],[26,0,26,13],[27,0,27,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财社〔2024〕41号-兰州新区第一人民医院-2024年第二批基本公共卫生服务补助资金（省级）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"486400",null,"486400",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"486400",null,"486400",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"逐步提高新区农村妇女自我保健意识和广大育龄夫妇自觉参与国家免费孕前优生健康检查的意识，降低新生儿遗传代谢病致畸率，确保项目检查目标人群覆盖率，减少出生缺陷发生，不断提高出生人口素质。通过职业病的主动干预和提前防治，有效降低职业病的发病，提升工作岗位人员的健康水平和幸福感。",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=95百分数","95","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"目标检查人数",null,"全额完成","100%-80%(含)","13.33","","100%","12",""]
["绩效目标","产出指标",null,"质量指标",null,"检查工作质量",null,"合格","100%-80%(含)","13.33","","100%","12",""]
["绩效目标","产出指标",null,"时效指标",null,"资金到位及时性",null,"及时","100%-80%(含)","13.34","","100%","12.01",""]
["绩效目标","效益指标",null,"社会效益指标",null,"妇女两癌保健意识",null,"有效提升","100%-80%(含)","5","","100%","4.5",""]
["绩效目标","效益指标",null,"社会效益指标",null,"新生儿健康水平",null,"有效提升","100%-80%(含)","5","","100%","4.5",""]
["绩效目标","效益指标",null,"社会效益指标",null,"育龄夫妇优生检查意识",null,"有效提升","100%-80%(含)","5","","100%","4.5",""]
["绩效目标","效益指标",null,"社会效益指标",null,"职业病发病率",null,"有效降低","100%-80%(含)","5","","100%","4.5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"相关职业病岗位人员",null,">=90百分数","90","5","百分数","100.00%","5",""]
[]
["总分",{"$nulls":8},100,null,null,"94.01"]

{"sheet":"2024年医疗服务与保障能力提升（公立医院综合改革）第二批补助","index":10,"n_rows":28,"n_cols":14,"rows_kept":28,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,25,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,21,2],[17,3,18,4],[17,5,17,6],[18,5,18,6],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,3,21,4],[21,5,21,6],[22,1,23,2],[22,3,23,4],[22,5,22,6],[23,5,23,6],[24,1,25,2],[24,3,25,4],[24,5,24,6],[25,5,25,6],[26,0,26,13],[27,0,27,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财社〔2024〕44号-兰州新区第一人民医院-2024年医疗服务与保障能力提升（公立医院综合改革）第二批补助资金（中央）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"1500000",null,"1500000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"1500000",null,"1500000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"深化以公益性为导向的公立医院改革，推动公立医院高质量发展，深入推广三明医改经验，促进医保、医疗、医药协同发展和治理",{"$nulls":5},"资金已全额支付完成，项目目标基本实现"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=100%","100","20","%","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"医院安防系统建设达标率",null,"=100%","100","8","%","100.00%","8",""]
["绩效目标","产出指标",null,"数量指标",null,"医院医疗服务收入占比",null,">=37.84%","38","8","%","100.42%","8",""]
["绩效目标","产出指标",null,"质量指标",null,"安防建设质量",null,"合格","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","产出指标",null,"质量指标",null,"医院服务能力",null,"有效提升","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","产出指标",null,"时效指标",null,"资金到位及时性",null,"及时","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","效益指标",null,"社会效益指标",null,"基层诊疗占比",null,"提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"医院资产负债率",null,"<=36%","30","10","%","83.33%","8.33",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90%","90","5","%","100.00%","5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"医疗机构满意度",null,">=90%","90","5","%","100.00%","5",""]
[]
["总分",{"$nulls":8},100,null,null,"94.93"]

{"sheet":"2024年重大公共卫生服务补助资金（中央）","index":11,"n_rows":25,"n_cols":14,"rows_kept":25,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,22,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,20,2],[17,3,18,4],[17,5,17,6],[18,5,18,6],[19,3,19,4],[19,5,19,6],[20,3,20,4],[20,5,20,6],[21,1,21,2],[21,3,21,4],[21,5,21,6],[22,1,22,2],[22,3,22,4],[22,5,22,6],[23,0,23,13],[24,0,24,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"甘财社〔2024〕66号-兰州新区第一人民医院-2024年重大公共卫生服务补助资金（中央）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"180400",null,"60872.4",null,"10","33.74","3.37"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"180400",null,"60872.4",null,"-","33.74","3.37"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"提升疾病防控能力，落实传染病综合防控措施，根据省财政厅、省卫健委、省疾控局《关于下达2024年重大公共卫生服务补助资金的通知》（甘财社【2024】66号），拨付资金用于医院开展艾滋病救治工作，有效控制艾滋病疫情，进一步减少结核感染、患病和死亡，切实降低结核病负担，提高人民群众健康水平，促进国民经济发展和社会和谐稳定",{"$nulls":5},"根据上级要求，积极开展项目工作，完成资金的部分支付，实现支付率33.74%，后期将加快支付"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=100百分数","98","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"艾滋病毒抗体筛查人数占总人口的比例",null,">=29百分数","29","10","百分数","100.00%","10",""]
["绩效目标","产出指标",null,"数量指标",null,"孕产妇艾滋病检测率",null,">=99百分数","95","10","百分数","95.96%","10",""]
["绩效目标","产出指标",null,"质量指标",null,"检测结果准确性",null,"=100百分数","100","10","百分数","100.00%","10",""]
["绩效目标","产出指标",null,"时效指标",null,"项目开展时限",null,"2024年","100","10","","4.94%","0.49",""]
["绩效目标","效益指标",null,"社会效益指标",null,"艾滋病感染率",null,"有效降低","100%-80%(含)","20","","100%","18",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90百分数","90","10","百分数","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"81.86"]

{"sheet":"2024年急救运转经费（本级）","index":12,"n_rows":33,"n_cols":14,"rows_kept":33,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,30,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,25,2],[17,3,19,4],[17,5,17,6],[18,5,18,6],[19,5,19,6],[20,3,22,4],[20,5,20,6],[21,5,21,6],[22,5,22,6],[23,3,25,4],[23,5,23,6],[24,5,24,6],[25,5,25,6],[26,1,28,2],[26,3,28,4],[26,5,26,6],[27,5,27,6],[28,5,28,6],[29,1,30,2],[29,3,30,4],[29,5,29,6],[30,5,30,6],[31,0,31,13],[32,0,32,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"兰新预〔2024〕1号-兰州新区第一人民医院-2024年急救运转经费（本级）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"920000",null,"920000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"920000",null,"920000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"加快建设与新区社会经济发展水平及人民健康需求相适应的院前医疗服务体系",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=90百分数","90","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"化工园区急救分站运行",null,"正常","100%-80%(含)","4.44","","100%","4",""]
["绩效目标","产出指标",null,"数量指标",null,"经费拨付率",null,"=100百分数","100","4.44","百分数","100.00%","4.44",""]
["绩效目标","产出指标",null,"数量指标",null,"新区急救中心运行",null,"正常","100%-80%(含)","4.44","","100%","4",""]
["绩效目标","产出指标",null,"质量指标",null,"急救运转和保障工作达标率",null,"=100百分数","100","4.44","百分数","100.00%","4.44",""]
["绩效目标","产出指标",null,"质量指标",null,"新区120急救中心有序运行",null,"有序","100%-80%(含)","4.44","","100%","4",""]
["绩效目标","产出指标",null,"质量指标",null,"足额拨付经费",null,"足额","100%-80%(含)","4.44","","100%","4",""]
["绩效目标","产出指标",null,"时效指标",null,"拨付经费及时性",null,"及时","100%-80%(含)","4.48","","100%","4.03",""]
["绩效目标","产出指标",null,"时效指标",null,"急救运转和保障工作及时性",null,"及时","100%-80%(含)","4.44","","100%","4",""]
["绩效目标","产出指标",null,"时效指标",null,"新区120急救中心运行及时性",null,"及时","100%-80%(含)","4.44","","100%","4",""]
["绩效目标","效益指标",null,"社会效益指标",null,"提升新区120急救调度能力",null,"提升","100%-80%(含)","6.66","","100%","5.99",""]
["绩效目标","效益指标",null,"社会效益指标",null,"有序进行救治和转运",null,"有序","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","效益指标",null,"社会效益指标",null,"院前急救和保障突发公共事件零差错",null,"零差错","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"各医疗机构满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"群众满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
[]
["总分",{"$nulls":8},100,null,null,"94.9"]

{"sheet":"2024年医师节护士节活动经费（本级）","index":13,"n_rows":28,"n_cols":14,"rows_kept":28,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,25,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,21,2],[17,3,18,4],[17,5,17,6],[18,5,18,6],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,3,21,4],[21,5,21,6],[22,1,24,2],[22,3,24,4],[22,5,22,6],[23,5,23,6],[24,5,24,6],[25,1,25,2],[25,3,25,4],[25,5,25,6],[26,0,26,13],[27,0,27,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"兰新预〔2024〕1号-兰州新区第一人民医院-2024年医师节护士节活动经费（本级）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"80000",null,"80000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"80000",null,"80000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"组织开展兰州新区卫生系统“512”国际护士节庆祝活动，包括义诊、讲座、表彰奖励等系列活动",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=90百分数","90","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"举办医师节护士节技能比赛活动",null,"=1次","1","8","次","100.00%","8",""]
["绩效目标","产出指标",null,"数量指标",null,"举办医师节护士节义诊和讲座活动",null,"=1次","1","8","次","100.00%","8",""]
["绩效目标","产出指标",null,"质量指标",null,"举办医师节护士节技能比赛达标率",null,"=100百分数","100","8","百分数","100.00%","8",""]
["绩效目标","产出指标",null,"质量指标",null,"举办医师节护士节义诊和讲座活动达标率",null,"=100百分数","100","8","百分数","100.00%","8",""]
["绩效目标","产出指标",null,"时效指标",null,"举办医师节护士节技能比赛、活动及时性",null,"及时","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","效益指标",null,"社会效益指标",null,"促进新区卫生事业健康稳定发展",null,"促进","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","效益指标",null,"社会效益指标",null,"提高医务人员干事创业积极性",null,"提高","100%-80%(含)","6.66","","100%","5.99",""]
["绩效目标","效益指标",null,"社会效益指标",null,"营造尊医重卫社会氛围",null,"营造","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"医务人员满意度",null,">=90百分数","90","10","百分数","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"97.19"]

{"sheet":"2024年急救运转经费","index":14,"n_rows":26,"n_cols":14,"rows_kept":26,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,23,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,19,2],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,3,19,4],[19,5,19,6],[20,1,21,2],[20,3,21,4],[20,5,20,6],[21,5,21,6],[22,1,23,2],[22,3,23,4],[22,5,22,6],[23,5,23,6],[24,0,24,13],[25,0,25,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"新财预〔2024〕1号-兰州新区第一人民医院-2024年急救运转经费"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"136400",null,"136400",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"136400",null,"136400",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"做好各类重大会议、会展、赛事、考试、应急演练、群众性活动等事项的医疗卫生保障",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,"<=100%","100","20","%","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"急救运转保障次数",null,"=130次","130","13.33","次","100.00%","13.33",""]
["绩效目标","产出指标",null,"质量指标",null,"急救运转保障工作质量",null,"合格","100%-80%(含)","13.33","","100%","12",""]
["绩效目标","产出指标",null,"时效指标",null,"保障工作开展及时性",null,"及时","100%-80%(含)","13.34","","100%","12.01",""]
["绩效目标","效益指标",null,"社会效益指标",null,"急救调度能力",null,"有效提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"县域内急救能力",null,"有效提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90%","90","5","%","100.00%","5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"医疗机构满意度",null,">=90%","90","5","%","100.00%","5",""]
[]
["总分",{"$nulls":8},100,null,null,"95.34"]

{"sheet":"2024年兰州新区健康中国中医药专项活动资金（本级）","index":15,"n_rows":29,"n_cols":14,"rows_kept":29,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,26,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,21,2],[17,3,18,4],[17,5,17,6],[18,5,18,6],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,3,21,4],[21,5,21,6],[22,1,24,2],[22,3,22,4],[22,5,22,6],[23,3,24,4],[23,5,23,6],[24,5,24,6],[25,1,26,2],[25,3,26,4],[25,5,25,6],[26,5,26,6],[27,0,27,13],[28,0,28,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"新财预〔2024〕1号-兰州新区第一人民医院-2024年兰州新区健康中国中医药专项活动资金（本级）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"100000",null,"100000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"100000",null,"100000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"为大力发展新区中医药事业，根据省财政厅、省卫生健康委员会《关于提前下达2024年中央转移支付医疗服务与保障能力提升(中医药事业传承与发展部分)补助资金预算的通知》(甘财社〔2023〕153号)，新区卫生健康委员会《关于印发〈2024年兰州新区健康中国中医药专项活动项目实施方案〉的通知》(新卫函〔2024〕45号)要求，医院1.进一步健全中医药服务体系，持续提升中医药服务水平，提高张西医结合服务水平，提高中药重点科室建设水平。\r\n2.开展中医药健康宣教、中医馆和中医重点科室服务能力提升等工作。\r\n3.打造1家“旗舰中医馆”和10家“旗舰中医阁”。",{"$nulls":5},"基本实现项目目标，执行率100%"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=95百分数","95","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"项目建设情况进度",null,"按时完成","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","产出指标",null,"数量指标",null,"中医服务能力提升",null,">=95百分数","95","8","百分数","100.00%","8",""]
["绩效目标","产出指标",null,"质量指标",null,"经费保证率",null,"=100百分数","100","8","百分数","100.00%","8",""]
["绩效目标","产出指标",null,"质量指标",null,"中医药服务能力提升达标率",null,"=100百分数","100","8","百分数","100.00%","8",""]
["绩效目标","产出指标",null,"时效指标",null,"中医药服务能力提升及时性",null,"及时","100%-80%(含)","8","","100%","7.2",""]
["绩效目标","效益指标",null,"经济效益指标",null,"中医药收入",null,"有效增加","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","效益指标",null,"社会效益指标",null,"新区中医药发展",null,"持续提升","100%-80%(含)","6.66","","100%","5.99",""]
["绩效目标","效益指标",null,"社会效益指标",null,"中医就诊人数",null,"显著提高","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"医院满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
[]
["总分",{"$nulls":8},100,null,null,"96.39"]

{"sheet":"2024年省政府为民办实事妇女“两癌”筛查项目-妇女两癌筛查经","index":16,"n_rows":25,"n_cols":14,"rows_kept":25,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,22,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,19,2],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,3,19,4],[19,5,19,6],[20,1,21,2],[20,3,21,4],[20,5,20,6],[21,5,21,6],[22,1,22,2],[22,3,22,4],[22,5,22,6],[23,0,23,13],[24,0,24,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"新财预〔2024〕1号-兰州新区第一人民医院-2024年省政府为民办实事妇女“两癌”筛查项目-妇女两癌筛查经费（本级）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"121000",null,"121000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"121000",null,"121000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"逐步提高新区广大育龄妇女自觉参与两癌检查的意识，确保项目检查目标人群覆盖率，增强新区妇女保健意识，提升妇女健康保障水平，促进经济社会和谐发展。",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=100百分数","100","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"妇女两癌检查人数",null,">=1100人","1100","13.33","人","100.00%","13.33",""]
["绩效目标","产出指标",null,"质量指标",null,"两癌检查完成率",null,">=100百分数","100","13.33","百分数","100.00%","13.33",""]
["绩效目标","产出指标",null,"时效指标",null,"资金到位率",null,">=100百分数","100","13.34","百分数","100.00%","13.34",""]
["绩效目标","效益指标",null,"社会效益指标",null,"妇女“两癌”防治知晓率和自我保健意识",null,"逐步提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"减少出生缺陷发生，不断提高出生人口素质",null,"逐步提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"服务对象满意度",null,">=80百分数","80","10","百分数","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"98"]

{"sheet":"2024年医政医改管理经费","index":17,"n_rows":28,"n_cols":14,"rows_kept":28,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,25,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,22,2],[17,3,19,4],[17,5,17,6],[18,5,18,6],[19,5,19,6],[20,3,21,4],[20,5,20,6],[21,5,21,6],[22,3,22,4],[22,5,22,6],[23,1,23,2],[23,3,23,4],[23,5,23,6],[24,1,25,2],[24,3,25,4],[24,5,24,6],[25,5,25,6],[26,0,26,13],[27,0,27,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"新财预〔2024〕1号-兰州新区第一人民医院-2024年医政医改管理经费"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"2000000",null,"2000000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"2000000",null,"2000000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"持续深化医药卫生体制改革，激发医疗服务质量快速提升，结合实际全面推广三明医改经验，继续推动兰州想新区紧密型县域医共体建设，以“保基本、强基层、建机制”为目标，建立一个责任、管理、服务、利益“四位一体”的紧密型县域医共体。加强牵头医院能力建设，推动优质医疗卫生资源下沉，让老百姓在家门口就近享受县级以上质优价廉医疗服务的目的。",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=95%","95","20","%","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"救治中心能力提升",null,"有效提升","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"数量指标",null,"县域医学中心能力",null,"有效提升","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"数量指标",null,"重点学科建设",null,">=3个","1","6.67","个","33.33%","2.22",""]
["绩效目标","产出指标",null,"质量指标",null,"紧密型县域医共体建设达标率",null,"=100%","100","6.67","%","100.00%","6.67",""]
["绩效目标","产出指标",null,"质量指标",null,"学科建设达标率",null,"=100%","100","6.67","%","100.00%","6.67",""]
["绩效目标","产出指标",null,"时效指标",null,"经费拨付及时性",null,"及时","100%-80%(含)","6.65","","100%","5.98",""]
["绩效目标","效益指标",null,"社会效益指标",null,"优质医疗资源下沉",null,"持续推动","100%-80%(含)","20","","100%","18",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90%","90","5","%","100.00%","5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"医疗机构满意度",null,">=90%","90","5","%","100.00%","5",""]
[]
["总分",{"$nulls":8},100,null,null,"91.54"]

{"sheet":"妇幼安全保障经费（本级）","index":18,"n_rows":29,"n_cols":14,"rows_kept":29,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,26,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,22,2],[17,3,19,4],[17,5,17,6],[18,5,18,6],[19,5,19,6],[20,3,20,4],[20,5,20,6],[21,3,22,4],[21,5,21,6],[22,5,22,6],[23,1,24,2],[23,3,24,4],[23,5,23,6],[24,5,24,6],[25,1,26,2],[25,3,26,4],[25,5,25,6],[26,5,26,6],[27,0,27,13],[28,0,28,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"新财预〔2024〕1号-兰州新区第一人民医院-妇幼安全保障经费（本级）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"180000",null,"180000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"180000",null,"180000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"为进一步促进基本公共卫生服务均等化，提升基层医疗机构服务质效，根据省委、省政府《关于优化生育政策促进人口长期均衡发展的实施方案》（甘发〔2022〕13号），省卫生健康委员会、省财政厅《关于做好2023年基本公共卫生服务工作的通知》（甘卫基层函〔2023〕317号）以及新区卫生健康委员会《关于转发<甘肃省推进家庭医生签约服务高质量发展若干措施>的通知》（新卫发〔2023〕37号）要求增强新区妇女儿童保健意识，提升妇女儿童健康保障水平，保障母婴安全，降低孕产妇和新生儿死亡率，促进经济社会和谐发展",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=95百分数","95","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"儿童健康管理率",null,"有效提升","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"数量指标",null,"婚检率",null,">=55百分数","55","6.67","百分数","100.00%","6.67",""]
["绩效目标","产出指标",null,"数量指标",null,"孕产妇死亡率",null,"有效降低","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"质量指标",null,"培训质量",null,"合格","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"时效指标",null,"项目进度保障",null,"有效保障","100%-80%(含)","6.65","","100%","5.99",""]
["绩效目标","产出指标",null,"时效指标",null,"项目开展及时性",null,"及时","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","效益指标",null,"社会效益指标",null,"妇幼工作人员能力",null,"持续提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"妇幼工作效果",null,"持续提升","100%-80%(含)","10","","100%","9",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"工作人员满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
[]
["总分",{"$nulls":8},100,null,null,"94.66"]

{"sheet":"数据中心卫生专网费用（本级）","index":19,"n_rows":27,"n_cols":14,"rows_kept":27,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,24,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,22,2],[17,3,18,4],[17,5,17,6],[18,5,18,6],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,3,22,4],[21,5,21,6],[22,5,22,6],[23,1,23,2],[23,3,23,4],[23,5,23,6],[24,1,24,2],[24,3,24,4],[24,5,24,6],[25,0,25,13],[26,0,26,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"新财预〔2024〕1号-兰州新区第一人民医院-数据中心卫生专网费用（本级）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"25000",null,"25000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"25000",null,"25000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"为进一步促进基本公共卫生服务均等化，提升基层医疗机构服务质效，根据省委、省政府《关于优化生育政策促进人口长期均衡发展的实施方案》（甘发〔2022〕13号），省卫生健康委员会、省财政厅《关于做好2023年基本公共卫生服务工作的通知》（甘卫基层函〔2023〕317号）以及新区卫生健康委员会《关于转发<甘肃省推进家庭医生签约服务高质量发展若干措施>的通知》（新卫发〔2023〕37号）要求，医院加快推进医共体信息化建设，保障基层医疗机构提升改造项目单位新区智慧城市智慧医疗数据中心与全省卫生专网链路通畅。",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=95百分数","95","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"医共体网络覆盖率",null,"=100百分数","100","6.67","百分数","100.00%","6.67",""]
["绩效目标","产出指标",null,"数量指标",null,"资金支付情况",null,"=100百分数","100","6.67","百分数","100.00%","6.67",""]
["绩效目标","产出指标",null,"质量指标",null,"网络运行",null,"有效保障","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"质量指标",null,"资金使用合规性",null,"合规","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","产出指标",null,"时效指标",null,"经费支出及时率",null,"=100百分数","100","6.65","百分数","100.00%","6.65",""]
["绩效目标","产出指标",null,"时效指标",null,"项目进度",null,"按时完成","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","效益指标",null,"社会效益指标",null,"医院系统运行",null,"有效保障","100%-80%(含)","20","","100%","18",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90百分数","90","10","百分数","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"95.99"]

{"sheet":"新区托育机构配套补助资金（本级）","index":20,"n_rows":25,"n_cols":14,"rows_kept":25,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,22,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,20,2],[17,3,18,4],[17,5,17,6],[18,5,18,6],[19,3,19,4],[19,5,19,6],[20,3,20,4],[20,5,20,6],[21,1,21,2],[21,3,21,4],[21,5,21,6],[22,1,22,2],[22,3,22,4],[22,5,22,6],[23,0,23,13],[24,0,24,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"新财预〔2024〕1号-兰州新区第一人民医院-新区托育机构配套补助资金（本级）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"500000",null,"500000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"500000",null,"500000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"为进一步促进基本公共卫生服务均等化，提升基层医疗机构服务质效，根据省委、省政府《关于优化生育政策促进人口长期均衡发展的实施方案》（甘发〔2022〕13号），省卫生健康委员会、省财政厅《关于做好2023年基本公共卫生服务工作的通知》（甘卫基层函〔2023〕317号）以及新区卫生健康委员会《关于转发<甘肃省推进家庭医生签约服务高质量发展若干措施>的通知》（新卫发〔2023〕37号）要求通过政府配套资金补助，由新区第一人民医院（新区妇幼保健院）在中川园区栖霞中心社区辖区内建设托育机构1个（托位50个），逐步构建新区普惠托育服务体系，解决辖区生育家庭托育需求，减轻托育经济负担，提升新区生育家庭获得感。",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=95百分数","95","20","百分数","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"建设托位",null,"=50个","50","10","个","100.00%","10",""]
["绩效目标","产出指标",null,"数量指标",null,"建设托育机构",null,"=1个","1","10","个","100.00%","10",""]
["绩效目标","产出指标",null,"质量指标",null,"托育服务水平",null,"有效保障","100%-80%(含)","10","","100%","9",""]
["绩效目标","产出指标",null,"时效指标",null,"项目开展及时性",null,"及时","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"惠普托育体系建设",null,"持续推进","100%-80%(含)","20","","100%","18",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"生育家庭满意度",null,">=90百分数","90","10","百分数","100.00%","10",""]
[]
["总分",{"$nulls":8},100,null,null,"96"]

{"sheet":"医养结合工作经费（本级）","index":21,"n_rows":28,"n_cols":14,"rows_kept":28,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,25,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,21,2],[17,3,18,4],[17,5,17,6],[18,5,18,6],[19,3,19,4],[19,5,19,6],[20,3,21,4],[20,5,20,6],[21,5,21,6],[22,1,23,2],[22,3,23,4],[22,5,22,6],[23,5,23,6],[24,1,25,2],[24,3,25,4],[24,5,24,6],[25,5,25,6],[26,0,26,13],[27,0,27,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"新财预〔2024〕1号-兰州新区第一人民医院-医养结合工作经费（本级）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"0",null,"180000",null,"180000",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"null",null,"180000",null,"180000",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"null",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"null",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"为进一步促进基本公共卫生服务均等化，提升基层医疗机构服务质效，根据省委、省政府《关于优化生育政策促进人口长期均衡发展的实施方案》（甘发〔2022〕13号），省卫生健康委员会、省财政厅《关于做好2023年基本公共卫生服务工作的通知》（甘卫基层函〔2023〕317号）以及新区卫生健康委员会《关于转发<甘肃省推进家庭医生签约服务高质量发展若干措施>的通知》（新卫发〔2023〕37号）要求，坚持以提升医养结合服务质量为抓手,统筹资源,推进建设规范化老年医学科，开展基层医务人员医养服务能力、营养改善指导、失能评估及安宁疗护服务能力培训，与社区养老服务机构开展签约合作，引领带动新区医养结合服务工作高质量发",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"成本控制率",null,">=95百分数","","20","百分数","","0",""]
["绩效目标","产出指标",null,"数量指标",null,"建设规范化老年医学科",null,"=1个","","8","个","","0",""]
["绩效目标","产出指标",null,"数量指标",null,"老年健康服务能力培训",null,">=2次","","8","次","","0",""]
["绩效目标","产出指标",null,"质量指标",null,"培训质量",null,"合格","","8","","","0",""]
["绩效目标","产出指标",null,"时效指标",null,"项目进度",null,"有效保障","","8","","","0",""]
["绩效目标","产出指标",null,"时效指标",null,"项目开展",null,"及时","","8","","","0",""]
["绩效目标","效益指标",null,"社会效益指标",null,"老年健康服务能力",null,"有效提升","","10","","","0",""]
["绩效目标","效益指标",null,"社会效益指标",null,"医养服务人才",null,"有效增加","","10","","","0",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90百分数","","5","百分数","","0",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"医院工作人员满意度",null,">=90百分数","","5","百分数","","0",""]
[]
["总分",{"$nulls":8},100,null,null,"10"]

{"sheet":"业务用房租赁费（占比70）（第一人民医院）","index":22,"n_rows":28,"n_cols":14,"rows_kept":28,"merged":[[0,0,2,13],[3,0,3,13],[4,0,4,1],[4,2,4,13],[5,0,5,1],[5,2,5,7],[5,8,5,9],[5,10,5,13],[6,0,6,1],[6,2,6,3],[6,4,6,5],[6,6,6,7],[6,8,6,9],[6,12,6,13],[7,0,10,1],[7,2,7,3],[7,4,7,5],[7,6,7,7],[7,8,7,9],[7,12,7,13],[8,2,8,3],[8,4,8,5],[8,6,8,7],[8,8,8,9],[8,12,8,13],[9,2,9,3],[9,4,9,5],[9,6,9,7],[9,8,9,9],[9,12,9,13],[10,2,10,3],[10,4,10,5],[10,6,10,7],[10,8,10,9],[10,12,10,13],[11,0,11,13],[12,0,12,1],[12,2,12,13],[13,0,14,1],[13,2,13,7],[13,8,13,13],[14,2,14,7],[14,8,14,13],[15,1,15,2],[15,3,15,4],[15,5,15,6],[16,0,25,0],[16,1,16,2],[16,3,16,4],[16,5,16,6],[17,1,20,2],[17,3,17,4],[17,5,17,6],[18,3,18,4],[18,5,18,6],[19,3,20,4],[19,5,19,6],[20,5,20,6],[21,1,23,2],[21,3,23,4],[21,5,21,6],[22,5,22,6],[23,5,23,6],[24,1,25,2],[24,3,25,4],[24,5,24,6],[25,5,25,6],[26,0,26,13],[27,0,27,8]]}
["项目支出绩效自评表"]
[]
[]
["(2024年度)"]
["项目名称",null,"业务用房租赁费（占比70）（第一人民医院）"]
["主管部门",null,"兰州新区卫生健康委员会",{"$nulls":5},"实施单位",null,"兰州新区第一人民医院"]
[{"$nulls":4},"年初预算数",null,"全年预算数",null,"全年执行数",null,"分值","执行率(%)","得分"]
["项目资金（元）",null,"年度资金总额：",null,"19186100",null,"19186100",null,"19186100",null,"10","100","10"]
["项目资金（元）",null,"其中：财政拨款",null,"19186100",null,"19186100",null,"19186100",null,"-","100","10"]
["项目资金（元）",null,"上年结转资金",null,"0",null,"0",null,"0",null,"-","0","0"]
["项目资金（元）",null,"其他资金",null,"0",null,"0",null,"0",null,"-","0","0"]
[]
["未完成原因分析",null,""]
["年度总体目标",null,"预期目标",{"$nulls":5},"实际完成情况"]
[null,null,"有效减轻医院非业务支出，进一步保障医院良性运作，更好的为广大新区老百姓解决看病远，看病难的问题。",{"$nulls":5},"项目资金全部支付完成，项目目标基本实现。"]
[null,"一级指标",null,"二级指标",null,"三级指标",null,"年度指标","实际完成值","分值","单位","完成率","得分","未完成原因分析"]
["绩效目标","成本指标",null,"经济成本指标",null,"年租赁金额",null,"=2740.87万元","2740.87","20","万元","100.00%","20",""]
["绩效目标","产出指标",null,"数量指标",null,"租赁面积",null,"=47584.58平方米","47584.58","10","平方米","100.00%","10",""]
["绩效目标","产出指标",null,"质量指标",null,"项目实施管理率",null,"=100百分数","100","10","百分数","100.00%","10",""]
["绩效目标","产出指标",null,"时效指标",null,"租赁及时性",null,"及时","100%-80%(含)","10","","100%","9",""]
["绩效目标","产出指标",null,"时效指标",null,"租赁时限",null,"2024年全年","100%-80%(含)","10","","100%","9",""]
["绩效目标","效益指标",null,"社会效益指标",null,"居民看病难",null,"有效解决","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","效益指标",null,"社会效益指标",null,"卫生事业工作",null,"有效推进","100%-80%(含)","6.66","","100%","5.99",""]
["绩效目标","效益指标",null,"社会效益指标",null,"医疗业务开展",null,"有效保障","100%-80%(含)","6.67","","100%","6",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"患者满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
["绩效目标","满意度指标",null,"服务对象满意度指标",null,"医院职工满意度",null,">=90百分数","90","5","百分数","100.00%","5",""]
[]
["总分",{"$nulls":8},100,null,null,"95.99"]